## Abstract
PROPOSED ROAD No. 5 (B) FROM BADI OMTI TO MALVIYA CHOWK JABALPUR (M.P.)
Based on UADD SOR Vol. I to IV w.e.f. 10 May 2012
Length of the Road =670 m, ROW 18m
Abstract Estimate
S.No. | Description of Item |  |  | SOR Item | Cost
1 | Detailed Estimate of Road |  |  | 5043346.029 | 5043346.029
2 | Detailed Estimate of Drain |  |  | 26864386 | 26864386
3 | Detailed Estimate of Footpath |  |  | 3733351.488 | 3733351.488
| Total |  |  |  | 35641083.517
Technical Summary
Provisions -
1 | Length of the Road | = | 1300 m
2 | Roadway Width | = | 13.50m
3 | Lane | = | 2 Lane without Median with Both SideDrain
4 | Width of Carriageway | = | 7.5 m
5 | GSB | = | 250 mm thick in full width
6 | DLC | = | 100mm thick
7 | PQC M- 30 | = | 200 mm thick
8 | Design period | = | 20 years
9 | CBR of Subgrade | = | 3.87 to 4.96 % (existing BT Road)

## Road 1
PROPOSED ROAD No. 5 (B) FROM BADI OMTI TO MALVIYA CHOWK JABALPUR (M.P.)
Length of the Road =670 m, ROW 18m
Provision -
1 | Proposed Carriageway (without divider) - 9m.
2 | RCC Covered Drain - Either side - Size 800x800mm. Under Cycle Track.
3 | RCC Service Duct. Either side
(i) Duct for Electrical cable Size 900x1200mm.
(ii)Duct for Other utilities Size 500x500mm.
4 | Pathway - 3.00m. on either side with Paver block
5 | R.C.C. NP2 Hume Pipe for Service duct of 300mm Dia across the road.
Detailed Estimate of Road
S.No. | UADD SOR Vol II & III, ITEM NO | Descriptions of Item | Measurement |  |  |  |  | Rate | Unit | Amount
|  |  | No. | L | B | H | Quantity
1 | 3.1, Vol III | Excavation
Excavation for roadway in soil including loading in truck for carrying of cut earth to embankment site with all lifts and lead upto1000 metres and as per relevant clauses of section-300
|  | For Proposed widening of road |  |  |  | Av.
|  | Road Ch. 0 to 670m = 670m | 2 | 670 | 1.3 | 0.475 | 827.45
|  | Total |  |  |  |  | 827.45 | 88.2 | cum | 72981.09 | 88.2
4 | 4.8 Vol III | Crusher Run Macadam Base | [10 empty] | 2.3 | 1.95
Crusher Run Macadam Base (Providing crushed stone aggregate, depositing on a prepared surface by hauling vehicles, spreading and mixing with a motor grader, watering and compacting with a vibratory roller to clause 410 to form a layer of sub-base/Base)
Road Ch. 0 to 670m = 670m
|  | i) For 53 mm maximum size | 2 | 670 | 1.3 | 0.25 | 435.5
|  | Total |  |  |  |  | 435.5 | 749.7 | cum | 326494.35 |  | 749.7
5 | 4.5 Vol III | WMM
|  | Providing, laying, spreading and compacting graded stone aggregate to wet mix macadam specification including premixing the Material with water at OMC in mechanical mix plant carriage of mixed Material by tipper to site, laying in uniform layers with paver in sub - base / base course on well prepared surface and compacting with vibratory roller to achieve the desired density and as per relevant clauses of section - 400. | [5 empty] | 855.9 | cum | 335470.005
|  | Road Ch. 0 to 670m = 670m | 2 | 670 | 1.3 | 0.225 | 391.95
|  | Total quantity |  |  |  |  | 391.95 |  |  |  | 855.9
7 | 5.2 (i) Vol III | Tack Coat
Providing and applying tack coat with bitumen emulsion using emulsion pressure distributor on the prepared bituminous / granular surface cleaned with mechanical broom and as per relevant clauses of section 503. '@0.25 kg per sqm ….
|  | Road Ch. 0 to 670m = 670m | 1 | 670 | 9.6 |  | 6432
|  | Total quantity |  |  |  |  | 6432 | 8.1 | sqm | 52099.2
8 | 5.6 (ii) Vol III | Dense Bituminous Macadam
Providing and laying dense bituminous macadam with hot mix plant batch using crushed aggregates of specified grading, premixed with bituminous binder, transporting the hot mix to work site, laying with mechanical paver finisher to the required grade, level and alignment, rolling with smooth wheeled, vibratory and tandem rollers to achieve the desired compaction complete in all respects and as per relevant clauses of section-507. (Only cement will be used as filler) (for Grading Ifor Grading II( 50-75mm thickness )
|  | Road Ch. 0 to 670m = 670m | 1 | 670 | 9.6 | 0.05 | 321.6
|  | Total quantity |  |  |  |  | 321.6 | 6460.2 | cum | 2077600.32
9 | 5.8 (iv) Vol III | Bituminous Concrete
Providing and laying bituminous concrete with hot mix plant using crushed aggregates of specified grading,premixed with bituminous binder,transporting the hot mix to work site,laying with a mechanical paver finisher to the required grade,level and alignment,rolling with smooth wheeled, vibratory and tandem rollers to achieve the desired compaction in all respects and as per relevant clauses of section-509.(Only cement will be used as filler).
|  | iv) for Grading II ( 30-45 mm thickness ) with 60/70 bitumen | 1 | 670 | 9.6 | 0.03 | 192.96
|  | Total quantity |  |  |  |  | 192.96 | 7403.4 | cum | 1428560.064
10 | 8.10 Vol III | Road Marking
Road Marking with Hot Applied Thermoplastic Compound with Reflectorising Glass Beads on Bituminous Surface (Providing and laying of hot applie thermoplastic compound 2.5 mm thick including reflectorising glass beads @ 250gms per sqm area, thickness of 2.5 mm is exclusive of surface applied glass beads as per IRC:35 .The finished surface to be level, uniform and free from streaks and holes and as per relevant clauses of section-800. a) Height upto 5m
|  | Marking | 5 | 670 | 0.1 |  | 335
|  | Total |  |  |  |  | 335 | 810 | Sqm | 271350
11 | 8.8 Vol III | Painting lines, dashes, arrows etc
Painting lines, dashes, arrows etc on roads in two coats on new work with ready mixed road marking paint conforming to IS:164 on bituminous surface, including cleaning the surface of all dirt, dust and other foreign matter, arcation at site and traffic control as per relevant clauses of section-800 & I.R.C.-67 including cost of paint etc. complete.
|  | lines, dashes, arrows | 1 | 670 | 0.1 |  | 67 | Sqm | 63 | 4221
|  | Total |  |  |  |  | 67
12 | 8.12 Vol III | Road Delineators
Road Delineators (Supplying and installation of delineators (road way indicators, hazard markers, object markers), 80-100 cm high above ground level, painted black and white in 15 cm wide stripes, fitted with 80 x 100 mm rectangular or 75 mm dia circular reflectorised panels at the top, buried or pressed into the ground and confirming toIRC-79 and the drawings as per relevant clauses of section-800 of specifications.
|  |  | 45 |  |  |  | 45 | No. | 262.8 | 11826
|  | Total |  |  |  |  | 45
13 | 8.20 Vol III | Road Stud
Road Markers/Road Stud with Lense Reflector (Providing and fixing of road stud 100x 100 mm, dia cast in aluminium, resistant to corrosive effect of salt and grit, fitted with lense reflectors, nstalled in concrete or asphaltic surface by drilling hole 30 mm upto a depth of 60 mm and bedded in a suitable bituminous grout or epoxy mortar, all as per BS 873 part 4:1973)
|  | Road Delineators= 670x3 =2010m /3 = 670No. | 670 |  |  |  | 670 | No. | 641.7 | 429939
|  | Total |  |  |  |  | 670
14 | 24.3 Vol II | Non-Pressure NP2 For Service Duct
Providing and laying non-pressure NP2 class (light duty) R.C.C. pipes with collars jointed with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including testing of joints etc. complete
| 24.3.4 | 300 mm dia. R.C.C. pipe Non-Pressure NP2 | 6X5 | 2.5 |  |  | 75 | 437.4 | RM | 32805
|  | Total | [7 empty] | 5043346.029

## Drain
PROPOSED ROAD 5 (A) FROM BADI OMTI TO MALVIYA CHOWK JABALPUR (M.P.)
Length of the Road =670 m
Length of Drain = 670 m Both Side
Length of Service Duct no.1 & 2 CH. 0 to 670m
Provision -
Drain internal dimension 800 mm wide x 800 mm deep
Service Duct no.1 & 2 internal dimension 900x1200 & 500x500mm deep
Detailed Estimate of Drain & Service Duct
S.No. | UADD SOR Vol II & III, ITEM NO | Descriptions of Item | Measurement |  |  |  |  | Rate | Unit | Amount
|  |  | No. | L | B | H | Quantity
1 | 2.8 Vol II | Excavation for Drain & Service Duct |  |  | av
Earth work in excavation by mechanical means ....drains (not exceeding 1.5 m in width or 10 sqm ....... excavated soil as directed, within a lead of 50 m. 2.8.1 All kinds of soil
|  | Drain CH. 0 to 670m | 2 | 670 | 1.3 | 1.15 | 2003.3 | 116.1 | Cum | 829987.29
|  | Service Duct CH. 0 to 670m | 2 | 670 | 2.4 | 1.6 | 5145.6
|  | Total Excavation |  |  |  |  | 7148.9 |  |  |  | 116.1
2 | 2.3 Vol III | Dismantling of existing structures
Dismantling of existing structures like culverts, bridges, retaining walls and other structure comprising of masonry, cement concrete, wood work, steel work, including T&P and scaffolding wherever necessary, sorting the dismantled material, disposal of unserviceable material and stacking the serviceable material with all lifts and lead 1000 meter.b) Cement Concrete Grade M-15 & M-20
Drain CH. 0 to 900m
|  | Footing | 2 | 248 | 1 | 0.15 | 74.4
|  | Wall | 4 | 248 | 0.15 | 0.8 | 119.04 | 234 | Cum | 45264.96
|  | Total Excavation |  |  |  |  | 193.44
2 | 2.27.1 Vol II | Crusher Stone Dust
Supplying and filling in plinth under floors including, watering, ramming consolidating and dressing complete
|  | Drain CH. 0 to 670m | 2 | 670 | 1.3 | 0.1 | 174.2
|  | Service Duct CH. 0 to 670m | 2 | 670 | 2.4 | 0.1 | 321.6
|  | Total |  |  |  |  | 495.8 | 565.2 | Cum | 280226.16 | 565.2
3 | 4.1.5 Vol II | Cement Concrete M-10 for Base of Drain & Service Duct
Providing and laying in position cement concrete .... Up to plinth level. 4.1.5 Cement concrete grade M-10 (Nominal Mix) with 40 mm maximum size of stone aggregate
|  | Drain CH. 0 to 670m | 2 | 670 | 1.25 | 0.1 | 167.5
|  | Service Duct CH. 0 to 670m | 2 | 670 | 2.2 | 0.1 | 294.8
|  | Total quantity of M 10 for base |  |  |  |  | 462.3 | 3175.2 | Cum | 1467894.96 | 3175.2
4 | 5.1.1 Vol II | Cement Concrete M-20 Drain & Service Duct
Providing and laying Plain / Reinorced cement concrete (mixed in concrete mixture) … RCC Grade M20 with 20mm maxumum size of aggregate.
Drain CH. 0 to 670m
|  | Footing | 2 | 670 | 1.2 | 0.2 | 321.6
|  | Wall | 2X2 | 670 | 0.2 | 0.8 | 428.8
Service Duct No. 1 CH. 0 to 670m
|  | Footing | 2 | 670 | 1.1 | 0.2 | 294.8
|  | Wall | 2X2 | 670 | 0.2 | 1.4 | 1125.6
Service Duct No. 2 CH. 0 to 670m
|  | Footing | 2 | 670 | 0.7 | 0.2 | 187.6
|  | Wall | 2 | 670 | 0.2 | 0.7 | 187.6
Precasted
|  | Top Slab Over Drain CH. 0 to 670m | 2 | 670 | 1 | 0.2 | 268
|  | Top Slab Over Service Duct CH. 0 to 670m | 2 | 670 | 1.8 | 0.2 | 482.4
|  | Total quantity of M20 (drain) |  |  |  |  | 3296.4 | 4255.2 | cum | 14026841.28 | 4255.2
5 | 5.20.6 Vol II | Reinforcement for Drain & Service Duct | [5 empty] | 54 | Kg | 7947218.502
Reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete. 5.20.6 Thermo-Mechanically Treated bars. kilogram
Steel required for drain walls and base
As per X-section shown
Drain CH. 0 to 670m
Outer Bars
|  | Main Bar 12mm dia 250c/c | 2x2700 | 2.86 |  | 0.888 | 13714.272
|  | Distribution bar 10 mm dia 250c/c | 15x2 | 670 |  | 0.617 | 12401.7
Inner Bars
|  | Main Bar 12mm dia 250c/c | 2x2700 | 2.6 |  | 0.888 | 12467.52
|  | Distribution bar 10 mm dia 250c/c | 15x2 | 670 |  | 0.617 | 12401.7
Service Duct CH. 0 to 670m
Outer Bars
|  | Main Bar 10mm dia 250c/c | 2x2700 | 5.6 |  | 0.617 | 18658.08
|  | Distribution bar 8mm dia 250c/c | 22x2 | 670 |  | 0.395 | 11644.6
Inner Bars
|  | Main Bar 10mm dia 250c/c | 2x2700 | 5.3 |  | 0.617 | 17658.54
|  | Distribution bar 8mm dia 250c/c | 2x21 | 670 |  | 0.395 | 11115.3
Top Slab Over Drain CH. 0 to 670m
|  | Main Bar 12mm dia 250c/c | 2x4465 | 0.92 |  | 0.888 | 7295.4528
|  | Distribution bar 12mm dia 250c/c | 2x2x5 | 670 |  | 0.888 | 11899.2
Top Slab Over Service Duct
|  | Main Bar 10mm dia 250c/c | 2x4465 | 1.9 |  | 0.617 | 10473.3282
|  | Distribution bar 10mm dia 250c/c | 2x9 | 670 |  | 0.617 | 7441.02
|  | Total quantity |  |  |  |  | 147170.713
6 | 20.1.1 Vol II | Form work for Drain & Service Duct
Centering and shuttering including strutting, propping etc.and removal of form for : 20.1.1 Foundations, footings, bases of columns, etc. For mass concrete.
Drain CH. 0 to 670m
|  | R.C.C. wall outer | 2X2 | 670 |  | 0.8 | 2144
|  | R.C.C. wall Inear | 2X2 | 670 |  | 0.8 | 2144
|  | R.C.C. Footing | 2X2 | 670 |  | 0.2 | 536
Service Duct No. 1 CH. 0 to 670m
|  | R.C.C. wall outer | 2X2 | 670 |  | 1.4 | 3752
|  | R.C.C. wall Inear | 2X2 | 670 |  | 1.4 | 3752
|  | R.C.C. Footing | 2X2 | 670 |  | 0.2 | 536
Service Duct No. 2 CH. 0 to 670m
|  | R.C.C. wall outer | 2X2 | 670 |  | 0.7 | 1876
|  | R.C.C. wall Inear | 2X2 | 670 |  | 0.7 | 1876
|  | R.C.C. Footing | 2X2 | 670 |  | 0.2 | 536
Top Slab Over Drain CH. 0 to 670m
|  | Through out length | 2X2 | 670 |  | 0.2 | 536
|  | Edge | 2X2 | 1 |  | 0.2 | 0.8
Top Slab Over Service Duct
|  | Through out length | 2X2 | 670 |  | 0.2 | 536
|  | Edge | 2X2 | 1.3 |  | 0.2 | 1.04 |  |  |  | 124.2
|  | Total quantity |  |  |  |  | 18225.84 | 124.2 | Sqm | 2263649.328
7 | 14.8 Vol III | PVC Pipe/Weep holes in drain wall
|  | Providing PVC Pipe in Brick masonry / Plain / Reinforced concrete abutment, .. as per clause 2706 of specifications. | [5 empty] | 117.9 | RM. | 39496.5
|  | PVC Pipe | 2 | 670 | 0.15 |  | 201
|  | PVC Pipe Percast Slab | 2 | 670 | 0.1 |  | 134
|  | Total quantity |  |  |  |  | 335 |  |  |  | 117.9
8 | 2.25 Vol II | Back Filling
|  | Filling by available excavated earth (excluding rock) in trenches, plinth, sides of foundations etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50 m and lift upto 1.5 m. | [5 empty] | 53.1 |  | 9072.135
Drain CH. 0 to 670m
|  | R.C.C. wall outer | 2x2 | 670 | 0.05 | 0.95 | 127.3
Service Duct CH. 0 to 670m
|  | R.C.C. wall outer | 2x2 | 670 | 0.05 | 0.65 | 43.55
|  | Total quantity |  |  |  |  | 170.85
|  | Grand Total | [7 empty] | 26864386

## Footpath
PROPOSED ROAD No. 5 (B) FROM BADI OMTI TO MALVIYA CHOWK JABALPUR (M.P.)
Length of the Road =670 m, ROW 18m
Detaild Estimate of Footpath
S. No. | UADD SOR ITEM No | Descriptions of Item | Measurement |  |  |  |  | Rate | Unit | Amount
|  |  | No. | L | B | H | Quantity
Paver Block for Foot Path
1 | 2.6, Vol 2, pg 15 | Earthwork excavation
|  | Earth work in excavation by mechanical means hydraulic excavator) / manual means over areas (exceeding 30cm in depth. 1.5m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50m and lift upto 1.5m, disposed earth to be levelled and neatly dressed. 2.6.1 All kinds of soil | [5 empty] | 114.3 | cum | 20676.87
|  | Road CH. 0 to 670m | 2 | 670 | 0.45 | 0.3 | 180.9 |  |  |  | 102.87 | 11.43
|  | Total |  |  |  |  | 180.9
2 | 2.27 Vol II, pg 19 | E/W Moorum filling
Supplying and filling in plinth under floors including, watering, ramming consolidating and dressing complete. 2.27.3 Moorum/Hard copra
|  | Road CH. 0 to 670m | 2 | 670 | 0.45 | 0.3 | 180.9 | 513 | cum | 92801.7
Total
3 | 4.1.4 Vol. II, pg 34 | M10 base for paver block
|  | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering All work up to plinth level. 4.1.4 Cement concrete grade M-10 (Nominal Mix) with 20 mm maximum size of stone aggregate | [5 empty] | 3235.5 | cum | 195100.65
|  | Road CH. 0 to 670m | 2 | 670 | 0.45 | 0.1 | 60.3 |  |  |  |  | 3235.5
4 | 11.47 Vol II, pg 136 | Paver Block for Foot Path
|  | Providing and laying 60mm thick factory made cement concrete interlocking paver block of M-30 grade reflective type rubber modulded glossy colour paving block made by block making machine with strong vibratory compaction and of approved size and shape laid in required colour and pattern over and including 60mm thick compacted bed of stone dust filling the joints with sand etc. all complete as per the direction of Engineer in charge including locking edges wherever required wihing cement concrete M15 grade or cement mortor 1:3 with pigment of required shade to match the colour /shade of block including cost of labour, material , etc. all complete. | [5 empty] | 513 | sqm | 2062260
|  | Road CH. 0 to 670m | 2 | 670 | 3 |  | 4020
5 | 11.49 Vol II, pg 137 | Kerb Stone for Foot Path
|  | Providing and laying 60mm thick factory made cement concrete interlocking paver block of M-30 grade reflective type rubber modulded glossy colour paving block made by block making machine with strong vibratory compaction and of approved size and shape laid in required colour and pattern over and including 60mm thick compacted bed of stone dust filling the joints with sand etc. all complete as per the direction of Engineer in charge including locking edges wherever required wihing cement concrete M15 grade or cement mortor 1:3 with pigment of required shade to match the colour /shade of block including cost of labour, material , etc. all complete. | [5 empty] | 4588.2 | cum | 1312638.138
Road CH. 0 to 670m
on the either side of road ends
|  | Kerb stone | 4 | 670 | 0.2 | 0.335 | 179.56
|  | base | 4 | 670 | 0.265 | 0.15 | 106.53
|  | Total |  |  |  |  | 286.09 |  |  |  |  | 4588.2
6 | 4.1.1, Vol II, pg 34 | M20 at outer peripheri for fixing pavers
Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering All work up to plinth level. 4.1.1 Cement concrete grade M-20 (Nominal Mix) with 20 mm maximum size of stone aggregate
|  | Road CH. 0 to 670m | 2 | 670 | 0.15 | 0.06 | 12.06 | 4135.5 | cum | 49874.13 |  | 4135.5
| Total | [8 empty] | 3733351.488